## Header
Project Estimation
Project Name:
Total Estimation (hours): | 272
See 'Estimates' worksheet for detailed estimation
Project parameters
Expected/Required duration (days) | 30
Dedicated PM | No
PM complexity personal PM's time, hrs/day | Normal | 2
time per team member, hrs/day |  | 0.75
QA complexity | None | 0%
Unit Test coverage | Low (below 40%) | 15%
Recommended QA team size | 0
Recommended Development team size | 1.1333
Estimated cost
Plarform/Technology
Operating System(s)
Programming Language
Framework
Database
Questions
Assumptions |  | Impact
Items not included to estimation
Risks | Probaility | Impact

## Project Estimation
# | Task | Min (man/hrs) | Median (man/hrs) | Max (man/hrs) | Workload (man/hrs) | Comments
Project requirements specification
| General business workflow specification |  |  |  | 0
| UI requirements specification |  |  |  | 0
| HW requirements specification |  |  |  | 0
| Performance requirements specification |  |  |  | 0
| OS compatibility specification |  |  |  | 0
| Others … |  |  |  | 0
0
| Subtotal: | 0 | 0 | 0 | 0
Project technical specification
| Project architecture |  |  |  | 0
| Project use cases (with GUI samples) |  |  |  | 0
| Project technologies |  |  |  | 0
| Others … |  |  |  | 0
| Subtotal: | 0 | 0 | 0 | 0
Coding
| POC back |  |  |  | 0
| Add new repository and environments | 1 | 2 | 2 | 2
| Add entities and EF context | 5 | 6 | 7 | 7
| Auto generate database and fill it with test data | 3 | 4 | 5 | 5
| Add a hook on saving to save changes to historical table | 4 | 6 | 7 | 7
| Map classes from historical table to display view models | 7 | 9 | 11 | 10
| Add visitor classes to make a specific mapping logic for different data types | 13 | 16 | 19 | 18
| Create infrastructure classes and projects | 6 | 8 | 10 | 9
0
| POC front |  |  |  | 0
0
| Add project | 1 | 1 | 2 | 1
| Add list pages for entities | 12 | 15 | 19 | 17
| Add add/edit pages layout for entities | 10 | 14 | 18 | 16
| Add add/edit pages save logic for entities | 12 | 16 | 18 | 17
| Display historical changes of entity layout | 12 | 18 | 22 | 20
| Display historical changes of entity logic | 8 | 10 | 15 | 12
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Unit Tests | 15 | 19 | 24 | 22
| BugFixing | 17 | 22 | 27 | 25
| Subtotal: | 126 | 166 | 206 | 188
Documentation
| Context Help system (or help file) |  |  |  | 0
| User Guide |  |  |  | 0
| Installation Guide |  |  |  | 0
| Administrative Guide |  |  |  | 0
| Subtotal: | 0 | 0 | 0 | 0
QA
| Test cases | 0 | 0 | 0 | 0
| Functional/Performance/Load Testing | 0 | 0 | 0 | 0
| Subtotal: | 0 | 0 | 0 | 0
Builds and Deployment
| Build management (Build script, regular builds) | 0 | 0 | 0 | 0
| Deployment | 4 | 5 | 6 | 6
| Subtotal: | 4 | 5 | 6 | 6
Project Management
| Progress tracking / reporting / communication / development process documentation / tracking changes | 72 | 76 | 80 | 78
| Subtotal: | 72 | 76 | 80 | 78
Project Total: |  | 202 | 247 | 292 | 272
Note on G4: AG: Automatically calculated. Do not edit it directly. Calculation is based on Min, Max and Median values

## Lists
QA complexity
Extra | 75%
High | 50%
Normal | 35%
Low | 20%
None | 0%
Unit Test coverage
High (above 50%) | 50%
Normal (40%-50%) | 30%
Low (below 40%) | 15%
None | 0%
Project Management complexity
High | 3 | 1
Normal | 2 | 0.75
Low | 1 | 0.5
None | 0 | 0

## Checkpoints
| Min | Mid | Max | Load
PM / Development | 55.38% | 44.44% | 37.74% | 40.21%
PM daily load (%) | 30% | 31.67% | 33.33% | 32.5%
PM daily load (hrs) | 2.4 | 2.5333 | 2.6667 | 2.6