## Header
Project Estimation
Project Name:
Total Estimation (hours): | 251
See 'Estimates' worksheet for detailed estimation
Project parameters
Expected/Required duration (days) | 30
Dedicated PM | No
PM complexity personal PM's time, hrs/day | Low | 1
time per team member, hrs/day |  | 0.5
QA complexity | None | 0%
Unit Test coverage | Low (below 40%) | 15%
Recommended QA team size | 0
Recommended Development team size | 1.0458
Estimated cost
Plarform/Technology
Operating System(s)
Programming Language
Framework
Database
Questions
Assumptions |  | Impact
Items not included to estimation
Risks | Probaility | Impact

## Project Estimation
# | Task | Min (man/hrs) | Median (man/hrs) | Max (man/hrs) | Workload (man/hrs) | Comments
Project requirements specification
| General business workflow specification |  |  |  | 0
| UI requirements specification |  |  |  | 0
| HW requirements specification |  |  |  | 0
| Performance requirements specification |  |  |  | 0
| OS compatibility specification |  |  |  | 0
| Others … |  |  |  | 0
0
| Subtotal: | 0 | 0 | 0 | 0
Project technical specification
| Project architecture |  |  |  | 0
| Project use cases (with GUI samples) |  |  |  | 0
| Project technologies |  |  |  | 0
| Others … |  |  |  | 0
| Subtotal: | 0 | 0 | 0 | 0
Coding
| POC back |  |  |  | 0
| Add new repository and environments | 1 | 1 | 2 | 1
| Add entities User, Organization, Subscription and EF context | 4 | 5 | 6 | 6
| Auto generate database and fill it with test data | 3 | 4 | 5 | 5
| Add a hook on saving to save changes to historical table | 4 | 6 | 7 | 7
| Map classes from historical table to display view models | 7 | 9 | 13 | 11
| Add visitor classes to make a specific mapping logic for different data types | 13 | 16 | 18 | 17
| Create infrastructure classes and projects | 3 | 6 | 8 | 7
| Create CRU Service for Users | 3 | 5 | 7 | 6
0
| Create CRU Service for Subscriptions | 3 | 5 | 7 | 6
| Filter History changes view model fields by UserRole | 7 | 12 | 15 | 14
| Add DI | 1 | 2 | 2 | 2
| Add simple Authentication system | 5 | 6 | 8 | 7
0
0
0
0
0
0
0
0
0
| POC front |  |  |  | 0
| Add project | 1 | 1 | 2 | 1
| Add simple Authentication system | 5 | 7 | 8 | 8
| Add infrostructure to make requests to server with authentication | 4 | 6 | 7 | 7
| List page for users | 3 | 4 | 5 | 5
0
| List page for subscriptions | 3 | 4 | 5 | 5
| Add/Edit page for users | 4 | 6 | 8 | 7
| Edit page for organization | 3 | 5 | 7 | 6
| Add/Edit page for subscription | 5 | 7 | 9 | 8
| Display historical changes of entity layout | 5 | 7 | 8 | 8
| Display historical changes of entity logic with filtration | 6 | 8 | 9 | 9
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Unit Tests | 14 | 20 | 25 | 23
| BugFixing | 17 | 23 | 29 | 26
| Subtotal: | 124 | 175 | 220 | 202
Documentation
| Context Help system (or help file) |  |  |  | 0
| User Guide |  |  |  | 0
| Installation Guide |  |  |  | 0
| Administrative Guide |  |  |  | 0
| Subtotal: | 0 | 0 | 0 | 0
QA
| Test cases | 0 | 0 | 0 | 0
| Functional/Performance/Load Testing | 0 | 0 | 0 | 0
| Subtotal: | 0 | 0 | 0 | 0
Builds and Deployment
| Build management (Build script, regular builds) | 0 | 0 | 0 | 0
| Deployment | 4 | 5 | 6 | 6
| Subtotal: | 4 | 5 | 6 | 6
Project Management
| Progress tracking / reporting / communication / development process documentation / tracking changes | 38 | 41 | 44 | 43
| Subtotal: | 38 | 41 | 44 | 43
Project Total: |  | 166 | 221 | 270 | 251
Note on G4: AG: Automatically calculated. Do not edit it directly. Calculation is based on Min, Max and Median values

## Lists
QA complexity
Extra | 75%
High | 50%
Normal | 35%
Low | 20%
None | 0%
Unit Test coverage
High (above 50%) | 50%
Normal (40%-50%) | 30%
Low (below 40%) | 15%
None | 0%
Project Management complexity
High | 3 | 1
Normal | 2 | 0.75
Low | 1 | 0.5
None | 0 | 0

## Checkpoints
| Min | Mid | Max | Load
PM / Development | 29.69% | 22.78% | 19.47% | 20.67%
PM daily load (%) | 15.83% | 17.08% | 18.33% | 17.92%
PM daily load (hrs) | 1.2667 | 1.3667 | 1.4667 | 1.4333